## Sheet1
Implementation Plan Update, January 2009
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
Goal A: Recruit a Sustainable Student Population.
AIM A1: Build On campus enrollments to 1450 FTE. .Fall 2009, 1280. Fall 2010, 1330. Fall 2011, 1380. Fall 2012, 1430.
1 | Use data-driven market sector analysis |  | Ongoing | Cannon/Adnissions
| Use Noel-Levitz (N-L) data & ongoing consultation to target highest yield students | Ongoing fees to consultant group. Staff on-site visits
2 | Use student friendly and persistent processes to communicate with prospective students | New marketing materials and communication templates | Ongoing | Cannon/Admissions | $7,000 (E&G)
| Revise communications in Admissions Application process for both new and transfer prospective students | Housing brochure, web application. View book template for biennium. Specialty publications such as Hobsons. | Initial viewbook revised for 2008. New materials to be ready eraly in cycle.
Streamline application processes for all prospective students
Adhere to recommendations in N-L plan
Consult w/ N-L rep monthly
3 | Plan strategic visiting schedule for recruiters in regional schools | $20k Adler Funds | Ongoing. Admissions has already adjusted much of its practice to develop revisit schedule. | Cannon/Admissions | $8,000 (E&G)
$12k, Or Ag Found.
$5k, Native American recruitment
$5k, Rural Access Funds
N-L targeted visitations for HS students
Target specific demographic region/schools
4 | Expand options for connecting to high school age students through on site visits or through campus conference events. | FFA. FBLA 4H conference. Other EOU student events (Lego Robotics, Math Modeling, Girls in Science etc) and HS/MS on campus visitations (cohort groups from egion) | Winter 2008 700-800 students on campus. Winter 2009, 2000 students on campus. Spring 2009, 200 HS?MS visitors
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
5 | Engage Academc Affairs in recruitment plan, to include transfer scholarship initiatives
Enhance/develop recruiting activities outside 12 county region
Develop coop arrangement between Admissions and Regional Staff for recruiting activities, both HS & CC)
6 | Restructure financial aid awards favoring fewer full awards | Exceed the 9% cap on remission with assumption that return will exceed the costs | Implemented | Cannon/FAO Director
Develop multiple awards:
- EOU Pride Grants
- transfer scholarship, merit-and need-based
- pgm-specific transfer scholarship
- 12-County Award
7 | Employ niche market initiatives | Existing budget | Stage 1: Fall of 2009 (Native American) Stage 2, Fall of 2010 | Cannon/Admissions
$40,000 for Nat Amer,
$60,000 for Int'l,
$3,000 Hobson's
| Retain Native American recruiter | Renewal of rural access POP
Develop Hispanic recruitment initiatives
| Contract w/ Hobson's for international recruitment initiatives |  |  |  | $6,000 (E/G)
8 | Utilize Regional staff to develop CC recruiting initiatives |  | Begun | Cannon/Kreiger/Koza/Admissions
AIM A2: Build Online enrollments to 920 FTE. Fall 2008: 730. Fall 2009, 770. Fall 2010, 820. Fall 2011, 870. Fall 2012, 920
1 | Employ pride grant opportunities, transfer scholarships, including progam and institutional specific awards | Exceed the 9% cap on remission with assumption that return will exceed the costs | Implemented | Mike Cannon/FA Director/Admissions Director
Engage Regional staff as appropriate
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
1 | Develop transfer recruitment plan in conjunction w/ Regional staff. Produce recruiting materials for Regional staff |  | Ongoing. Initial work complete.
2 | Develop WEB Footprint that accentuates options | R&D, reinvestment | Stage 1: Winter 2008, Stage 2 Fall 2008 | Cannon/Seydel (Integrated Marketing Team), Registrar | $25,000 (E&G)
| Enhance WWW presence for student-friendliness |  | Initial overhaul complete.
Enhance web-accessible course listings for both on- and off-campus courses
3 | Develop program & institution specific advising sheets / information for CC transfer to online degree completion programs | Rural Initiative/ongoing reinvestment in existing regional staff | Initial work on transfer sheets begun. | Deans, DES (ACA & Regional Staff)
AIM A3: Build On site enrollments to 410 FTE. Fall 2008: 335. Fall 2009, 360. Fall 2010, 385. Fall 2011, 410. Fall 2012, 410
1 | Employ pride grant opportunities | Exceed the 9% cap on remission with assumption that return will exceed the costs | Implemented. | ED & BUS Deans
2 | Develop curricular grab sheets/advising information for CC transfer | Rural Initiative | Stage 1: Spring 2008, Stage 2: Fall 2008 | Deans
AIM A4: Build transfer enrollments from community colleges
1 | Develop marketing, admissions pathways, and financial aid keyed to encourage students from community colleges that do not traditionally transfer to EOU. | See A1, 2, 3 above. | Scholarships developed. | Enrollment management
AIM A6: Build Graduate Enrollments
1 | Increase graduate enrollment by filling current capacity of MTE, MS and MBA cohorts | See A1, 2, 3 above | Fall 2009 | Graduate program faculty
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
2 | Build a business plan to grow the MTE program to a new cohort in the mid-Columbia basin | 2.5 FTE Faculty, collaboartive with Columbia Gorge College | Fall 2011 | Dean, College of Ed & Bus | Self support
3 | Build a business plan to grow the MBA program to a new distance cohort | 1.5 New FTE | Fall 2011 | Dean, College of Ed & Bus | Self support
4 | Build marketing campaign for existing MBA/MTE programs | Print media | Fall 2009 | Dean, College of Ed & Bus
AIM A7: Address critical staffing measures in Enrollment Services
1 | Implement EOU Call Center, 5days/week, 12 hours/day |  | Complete
| Increase FTE of ACA receptionists from 0.5 to 0.75 | ~$42,000 reinvestment | Complete |  | $42,000 in 2007/8 E&G
Add 1.0 FTE: 0.4 FTE for Call Center, 0.6 FTE to rotate amongst DES units as-needed
AIM A8: Improve EOU Marketing Footprint
1 | Produce print communications on par with competitors | Outsource media | Winter 2009 | Tim Seydel | $19,088 (E&G)
2 | Graphic Artist | Transition from outsource to additional graphic artist |  |  | $35,490 (E&G)
3 | Broaden the reach of who and how we reach. |  | Fall 2010 |  | $75,000 (E&G)
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
AIM A9: Improve Student Services to retain students
1 | Establish compliance coordinator position for Athletics (also meets Goal B) | Improve timelines and predictability of admissions for athletic recruiting. Improve timeliness and accuracy of determining eligibility status for new and returning student athletes. | 2008-07-01 | Rob Cashell, AD Dean of Students | .25 FTE added to a current .5 FTE coaching position $13,866 including OPE (2007-8 E&G)
2 | Fully fund Men’s and Women’s Basketball coaching positions (also meets Goal B) | Use E&G funds to pick up that portion of coaches salaries paid by Booster Club funds. Reallocate these Booster Club funds to student scholarships for recruiting and retaining students. | 2008-07-01 | Rob Cashell, AD Dean of Students | $12,000 including OPE (2007-8 E&G)
3 | Move part-time head coaching positions to full-time status (Softball, Volleyball, and Soccer) | Part-time head coaches have full time obligations in recruiting, coaching, supervising, and mentoring students in their respective sports. Improvements in recruiting and retention can be gained by investing in full-time positions. | 2009-07-01 | Rob Cashell, AD Dean of Students | 2 positions from .50 FTE to 1.0 FTE ($42,550), 1 position from .75 FTE to 1.0 FTE (see A4) ($10,638), TOTAL: $53,188 including OPE
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
5 | Establish a .25 FTE assistant coach for Women’s Basketball (see E4 for Men’s Basketball) | Use E&G funds to pick up a portion of assistant coach stipend allowing Booster Club funds to be used for recruitment and retention of students. | 2009-07-01 | Dean of Students, Rob Cashell, AD | .25 FTE, $10,637 including OPE
6 | Reinstate support for Ambassador Program operations. This allows for a more professional presence with prospective students and families supporting EOU recruiting efforts. | (a) Name tags on jackets and shirts (embroidery) $300.00 | 2008-07-01 | Hailey Wolcott, Stephen Jenkins | 5500
7 | Initiate new training and incentive programs for Ambassadors to increase effectiveness and involvement. | (a) Develop and implement fall and winter retreats for team building and recruiting of student leaders for the ambassador Program. $1,800, (b) Develop a tuition waiver program for Ambassadors tied to service levels. $2,400 | 2008-07-01 | Stephen Jenkins, Hailey Wolcott, Admissions | 2008-07-01
AIM B1: Improve Freshman Retention to 85%. Fall 2008: 65%. Fall 2009, 68%. Fall 2010, 73%. Fall 2011, 78%. Fall 2012, 85%
1 | Establish First Year Experience Curriculum/Developmental |  | Fall 2008 | Sarah Witte | $55,000 (Rural Access)
2 | Reintroduce mandatory advising | Advising changes: revise campus advisers' PDs, revise faculty/adviser relationships | Fall 2009 | Mike Cannon
3 | Establish Eastrek Year for all freshmen |  | Fall 2008 | Michael Jaeger/Sarah Witte | $45,000 (Rural Access)
4 | Failure notice advising |  | Fall 2009 | Mike Cannon
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
| Fall 2008 | Michael Jaeger/Sarah Witte | $25,000 (Rural Access) |  |  |  | 6
Establish reduced fees for required developmental courses |  | Fall 2008 | Michael Jaeger/Sarah Witte
7 | Implement mandatory follow-through w/ placement scores & necessary dev-ed courses |  | Fall 2008 | Mathematics Faculty
8 | Reduce 100-level options for incoming freshmen, establish patterns for cohorts |  | Fall 2009 | Deans
9 | Provide professiona developmemnt for 100-level professors to assist in transition of freshmen students
10 | Install Scheduling software to maximize on-campus efficiency | $60,000 for Adastra software | Fall 2008 | IT/Registrar | 10000
11 | Establish a full-time live-in area coordinator for Residence Life. | Add an additional professional staff member to Residence Life will allow the Director of Housing and Student Life to be more involved with institution-wide initiatives like Affirmative Action Officer, CORE 102 instructor, and EasTrek Hum110 instructor of record. | July 1, 2009, Sept. 1, 2008 possible with a subsidy | Stephen Jenkins Director Housing and Student Life Dean of Students | $27,200 including OPE (Residence Life (auxiliary))
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
12 | Reinvest in Hoke Union Building operations. | Partner with Hoke Union in funding student manager positions. A shared funding source with E&G would allow for more leadership training opportunities for students, better service and programs for students at the HUB, and increasing late night events in the HUB. This supports retention efforts. | 2009-09-01 | Stephen Jenkins, | 15000
13 | Reinstate Assistant Athletic Director position. | Assistant Athletic Director would be assigned supervision of athletic training, equipment manager, dance team and intramural programs. This allows for program enhancement and service improvements for students. This also allows more effective use of Athletic Director’s time for supervising coaches, marketing and fund raising. | 2009-07-01 | Rob Cashell
14 | Establish compliance coordinator position for Athletics (also meets Goal B) | Improve timelines and predictability of admissions for athletic recruiting. Improve timeliness and accuracy of determining eligibility status for new and returning student athletes. | 2008-07-01 | Rob Cashell, AD Dean of Students | 25 FTE added to a current .5 FTE coaching position $13,866 including OPE.
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
Goal C: Ensure that University Technology and Information systems- retain adequacy and competitiveness
1 | Ensure the data stream beyond campus has a minimum 30 megabit capacity | Student Tech Fee funded annually at $19,000 | Spring 2008 | Paul Rowan
2 | Banner FIS and SIS Database Integration | OUS Funded at $50,000 | Spring to Winter 2008 | Paul Rowan
3 | Student e-mail | 2007-2009 COPS Student E-mail $35,000 | Spring 2009 | Paul Rowan
5 | Rewire Head Start in Ackerman to campus network standards | $5000 from IT | Fall 2008 | Paul Rowan
6 | Streaming video and audio media servers | 2007-2009 COPS Media Servers $30,000 | Winter 2008 | Paul Rowan
7 | IT Servers Back-up | 2007-2009 COPS Server Back-up $35,000 | Fall 2009 | Paul Rowan
8 | Fully fund Blackboard in regular budget |  | Spring 2008 | Paul Rowan | $110,000 (2007-8 E&G)
11 | IT Professional Development, Keep IT staff current in software/hardware education. |  | Winter 2009 | Paul Rowan | $10,000 (E&G)
12 | Ensure replacement of hardware/software (Operating systems and applications) | 2009-2011 COPS | Summer 2009 | Paul Rowan | $26,000 (E&G)
13 | Establish permanent budget for Blackboard support and software lease. | Redistribution of SS to IT | Summer 2008 | Cabinet | 75000
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
Goal D: Add Programs to EOU that will attract and retain new students
Aim D1, Business Programs
1 | Allocate a 1.0 FTE resource faculty position to College of Business. Load would be approx. ½ online and ½ on-campus to help reduce overload problems. | Reinvestment from BART savings & savings from in-loading some overload. | Search regionally this spring for position beginning Fall 2008 |  | 30000
2 | Discontinue Chemeketa program and transfer 1.0 FTE position to La Grande. | No additional cost . | Close Chemeketa effective July 1, 2009.
3 | Hire two FTE faculty positions for 2009-10 Academic year by re-assigning overload to create the two new positions. Will help reduce overload problems. | approx. $70,000 + $35,000 OPE or $210,000. This would be offset partially by in-loading a significant amount of overload. Approx. $35,000 per position. Net costs approx. $140,000. | Search beginning Fall 2008 for the 2009-10 Academic year. |  | 105000
4 | Hire additional adjunct faculty to teach on-line & on-site geography classes. Faculty retirement has created this need. | Courses are taught both as per student/per credit and by the course. Should be no additional cost. | Currently talking with prospective adjuncts to teach in 2008-09 Academic year.
5 | Fire Service Administration: Expand geographical area served and recruit more students in areas of emergency management and homeland security. | Taught by adjuncts, no additional resources committed. | Some steps already being taken. Will do more planning with.5 FTE program administrator in Summer 2008. |  | $25,000 (E&G)
Aim D2, Liberal Studies
1 | Develop LS programs to attract new student populations on campus, ie Environmental Studies, Human Services, and pre-planned, named LS programs | .25 FTE to coordinate/teach capstones, and provide academic leadership | Fall 2009 | Provost/ Liberal studies Committee | 8000
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
2 | Transition two minor LS degree formats to pre-approved, robust, named LS degrees | Strategic professional Program Development, $10,000. Rural Initiative | Implement Fall 2008/Winter 2009 | Mary Koza/Deans/LS Committee
Aim D3, Arts and Sciences
1 | Modify the Media Arts program to accommodate communications. Add the Communications minor and consider adding a Major. Would need 1.fte | Strategic professional development, Rural Access, $1000 *$5,000 ; If 1 FTE for a major add $65,000 | Implement Fall 2008 | CAS Dean/April Curtis | 65000
2 | Add Public Administration | Strategic professional development, $2000. Rural Access | Implement Fall 2008 | CAS Dean
3 | Pilot Digital Arts at Chemeketa Comm. College | Strategic professional development and per student- 2 courses a term | Implement Fall 2008 | CAS Dean/Art Faculty
4 | Promote newest EOU Program-Modern Languages and Global Cultures with possible development of International Certificate (no cost), innovative weekend colleges, and recruitment activities | $3,000 for materials and travel | Implement Fall 2008/Winter 2009 | CAS faculty, Enrollment services
5 | Program in development: Molecular Biology - monitor student interest, enrollment and recruitment | If program develops well and as state initiatives develop, consider more support. Health Initiative if in EBL, if recurring, then funded. | ongoing | Biology faculty, CAS Dean
Aim D3, Education
1 | Offer a teacher eductaion librarian cognate in the MS and seek TSPC approval for the endorsement | Self-support | Summer 2008 pilot | College of Education
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
2 | Re-assign current adjunct and overload to create an additional full time position | To convert from adjunct/overload pay to a full-time position would cost $15,000-20,000 depending on the rank of the position | Implement Fall 2009 | College of Education Dean and PHYSH faculty
3 | Add a middle level institute for those trying to add middle level authorization. Time frame would be weekend college or summer intense session or other alternative time frame. | In conjunction with PrISM program, funds for recruiting and marketing, self-support through tuition dollars | Implement Summer 2009 | College of Education Dean and Faculty, assistance from Admissions and Advising
4 | Add MTE Cohort in The Dalles | 2.0 FTE plus adjunct support, $165,000. Initial support, revenues thereafter (11 student break even point) | Implement Summer 2010 | College of Education Dean and Faculty
5 | Increase participation in the ECED Liberal Studies concentration | .25 FTE to coordinate plus funds for marketing and recruitment | Implement Fall 2008 | College of Education Dean and .25 Faculty, assistance from Admissions and Advising
6 | Increase the use of credit overlay | Develop a streamlined process and website information. About 10 hours of staff time for start up and then revenues | Implement Fall 2008 | College of Education Dean, assistance from Enrollment Services
7 | Increase the diversity of the teacher preparation students, especially at Ontario, Pendleton and Coos Bay | Rural Initiative Funds, partner with ESDs and districts with "grow-your-own" vision, target recruiting and scholarship dollars | Implement Fall 2008 | Admissions and Advising with support from College of Education Dean and Faculty
8 | Install a transitional license program within the MTE program | 3 load credits per term for an adviser | Implement Fall 2008 | College of Education Dean and MTE adviser
9 | PHYSH faculty member to accommodate growth in online degree program and potential for continued growth justifies additional FTE. | .5 FTE plus inload online instruction | Implement Fall 2009 | College of Education Dean and Division Chair | $30,000 (E&G)
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
Goal E: Modify Course/Program Delivery to accommodate efficient use of resources
1 | Support strategic professional development for faculty who need to move current on campus courses to alternative delivery | $5,000 Rural Initiative | Stage 1 Fall 2009, Stage 2, Fall 2010 | Deans
2 | Support strategic professional development for faculty who need to combine online with on campus courses in one delivery mode | $5,000 Rural Initiative | Stage 1 Fall 2009, Stage 2, Fall 2010 | Deans
3 | Support strategic professional development for faculty to develop new courses that would be available online to either in load or to continue as overload | $5,000 Rural Initiative | Stage 1 Fall 2009, Stage 2, Fall 2010 | Deans
4 | Spanish for Health professionals - alternative sites and modes of delivery | $8,000 Health Initiative | Fall 2008-Summer 2009 | Deans/ ML faculty
Goal F: Establish Partnerships
1 | Establish Sustainable Energy Degree Program with OIT/Community Colleges/ and Public and Private partners | POP/Other Grant funds | Fall 2009 | Provost and Deans
2 | Establish PCC Rock Creek Collaborative with PSU to offer Business Administration | 1.0 FTE initial investment $85,000 per annum. | Fall 2009 | Provost and Bus Dean
3 | Increase communication w CC by EOU faculty - travel, etc. *could multipurpose for recruitment | $5,000 per year | Fall 2008 | Faculty/Admissions
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
Goal G: Create University Assessment Model
1 | Develop standards for reporting enrollment data and post these data with benchmarks to a University dashboard | Farooq Sultan's time | Winter 2008 | Provost
2 | Develop standards for reporting admission data and post these data with benchmarks to a University dashboard | Admissions efforts | Fall 2008 | Provost
3 | Develop standards for reporting enrollment trends and goals to be used in assessment and post these data with benchmarks to a University dashboard | Farooq Sultan's time | Fall 2008 | Provost
4 | Develop standards for reporting programmatic enrollments and post these data with benchmarks to a University dashboard | Farooq Sultan's time | Begun Winter 2008, posting Fall 2008 | Provost
5 | Develop standards for reporting programmatic achievements and post these data with assessment summaries to a University dashboard | Kris Olson website posting | Summer 2008 | Provost
6 | Develop standards for tracking revenues, expenditures and reserves in real time with regular updates to dashboard | 1.0 FTE Finance $60,000 Reinvestment | Fall 2009 | Provost and VP Finance
7 | Develop entrepreneurial accounting system for program start-up for revenue positive operations. |  | Summer 2008 | Provost and VP Finance
8 | Develop tracking system to account for retention initiatives. | Programming time | Summer 2008 | Provost
9 | Develop standards for tracking efficiency savings from the shift of adjunct online pay to in load |  | Summer 2008 | Provost and VP Finance
10 | Develop tracking system for utility consumption by building |  |  | Physical plant
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
11 | Develop University assessment system for energy consumption by building
GOAL H: Integrate DDE into the College Structure
1 | Integrate scheduling of DDE and on-campus, onsite, and WEC courses - Abolish blue sheets, changeover accounting, refine CRN assignments, develop hybrid models of delivery |  | Summer 2008 | Deans (Academic/Enrollment Services)
2 | Plan for Instructional Budgets |  | Summer 2008 | Provost and VP Finance
3 | Move Service and supply budget to A&S and CEB to accommodate additional staff time and other expenses. Support A&S and ED-BUS with extrat staff time in order to inegrate blue sheet process and schedule/load and contract. |  | Fall 2008
4 | Macro assessment of integrated efficiencies by tracking College expenditures for online instruction as ratio of expenses/total SCH | Finance office | Summer 2008 | Provost and VP Finance
5 | Develop parallel course assessment tool that can be ported from Blackboard to a simple online evaluation system. | Programming time | Summer 2008 | Provost
6 | Develop hybrid numbering system for online/on campus course in same section. Develop one fee structure for such classes. | Policy development | Summer 2008 | Mike Cannon
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements
GOAL I: Maintain adequate library resources for all students
1 | Upgrade Summit (library resource sharing system) to enhance ease of use | $20,000 over a 2-3 year period to build up Orbis-Cascade reserve funds | Fall 2009 and Fall 2010 | Karen Clay
2 | Maintain library collection by increasing materials budget 6% annually (match expected inflation) | Annual budget increase $25,000 per year (note, this increase centrally allocated by OUS) | FY 2008/09 and 2009/10 | Karen Clay
3 | Introduce information literacy outcomes as a formal graduation requirement | Librarian effort to initiate and sustain collaborative efforts with faculty. | Initiate discussions with EPCC fall 2008. | Karen Clay
4 | Convert Library Systems technician to librarian position |  | Fall 2008 | Karen Clay | $5-7,000 per year
GOAL J: Ensure safe campus and reliable maintenance of facilities
1 | Assistant Director Physical Plant. Combine current positions into new position with greater responsibility. |  | Fall 2008 | Virginia Key | 15000
2 | Student Accounts Specialist 1.0 FTE. Pilot program to explore what proportion of bad debt may be returned to the University with added attention and persistence. |  | Fall 2008 | Virginia Key | 36000
3
4
Dean of Students
| STRATEGIES: This position would replace the Student Hall Director position in Alikut Hall and assume new duties as area coordinator for North and South Halls. This would align Residence Life more with CAS Standards. It would help create and implement Freshman Live-in Learning Communities and improve the social climate and student leadership in the residence halls thereby improving retention. Adding an additional professional staff member to Residence Life will also allow for the Director of Housing and Student Life to be more involved with institution wide initiatives like Affirmative Action Officer, CORE 102 instructor, and EasTrek Hum110 instructor of record. |  |  |  |  | Dean of Students
| AIMS/Strategies | Resources Required | Time Frame | Assessment Data/Reporter | New Recurring Budget Requirements